## Project Proposal
Academic /Industry | Deliverables | Activity | Estimated Time (hrs) | Actual Time (hrs)
Academic | Curriculum Vitea and Cover Letter | Updating CV and Cover Letter for the possible projects | 3 | 5
Academic | WIL and Supporting Documents | Signed by people involved | 1 | 2
Academic | Weekly Academic Supervisor Meetings | Weekly review of Risk Assessment, Burndown Chart and Progress Report | 0.75 | 0.75
Academic | Project Proposal | Project Details | 2 | 2
Academic |  | Project Scope | 1 | 1
Academic |  | Stakeholder Management | 2 | 2
Academic |  | Student Required Skills | 2
Academic |  | Project Plan | 2
Academic |  | Burndown Chart | 2
Academic |  | Risk Management | 2
Academic |  | Quality Assurance | 2
Academic |  | Professionalism | 2
Academic |  | Sustainability, Inclusive Practive and Te Tiriti o Waitangi | 3
Academic |  | Reflections | 2
Academic |  | References | 2
Academic |  | Appendices | 2
Academic | Weekly Academic Supervisor Meetings | Weekly check in | 0.75 | TBA
Academic | Weekly Academic Supervisor Meetings | Weekly check in | 0.75 | TBA
Academic | Weekly Academic Supervisor Meetings | Weekly check in | 0.75 | TBA
Academic | Project Proposal Checklist | Checking requirements needed for checklist | 1 | TBA
Academic | Project Proposal Signoff | Following Ara's sign off document | 1 | TBA
Academic | Project Proposal Update | Update Project Proposal based on Feedback from David | 10 | TBA
Academic | Halfway Repport | Progress update, reflections, what went well and didn't go well, improvements | 10 | TBA
Academic | Methodology Essay | 3,000 word document covers the topics in the marking guide based on the projects Methodology - Kanban | 10 | TBA
Academic | Final Report | Final reflections and self evaluation | 10 | TBA
Academic |  | Review final report document | 2 | TBA
Academic |  | Get and Apply feedback | 30 | TBA
Academic | Short Paper | Includes Introduction, Title, Author, Methodology, Process, Conclusions and Reflections | 10 | TBA
Academic | Poster | A1 format poster including: Introduction, Title, Author, Methodology, Process, Conclusions and Reflections | 10 | TBA
Academic | Short Biography | Professional writing of background and achievements | 10 | TBA
Academic | Panel Presentation | Creating Powerpoint | 10 | TBA
|  | Practice for presentation | 3 | TBA
|  | Presentation | 1 | TBA
|  | Total Hours: | 151 | 12.75
Industry | Discovery | Find out what is currently being used | 2 | TBA
Industry |  | Find out what data is needed | 2 | TBA
Industry |  | Find out how SharePoint works | 20 | TBA
Industry |  | TBA | TBA | TBA
|  | TBA | TBA | TBA
Industry |  | TBA | TBA | TBA
Industry |  | TBA | TBA | TBA
Industry | Design | Generate Iterations of Low-fi Designs | 2 | TBA
Industry |  | Get feedback |  | TBA
Industry |  | Generate iterations of high-fi designs |  | TBA
Industry |  | Get feedback |  | TBA
Industry |  | Generate user tests |  | TBA
Industry |  | Get feedback |  | TBA
Industry |  | TBA |  | TBA
Industry | Develop and Build (Per Iteration) | Have weekly meeting |  | TBA
Industry |  | Check MS Planner |  | TBA
Industry |  | Plan for iteration |  | TBA
Industry |  | Build iteraetion |  | TBA
Industry |  | Get feedback |  | TBA
Industry |  | Apply Feedback |  | TBA
Industry |  | Create small development document for iteration |  | TBA
Industry | Test and Review | Plan software t ests |  | TBA
Industry |  | Plane user tests |  | TBA
Industry |  | Develop Software tests |  | TBA
Industry |  | Develop User tests |  | TBA
Industry |  | Apply test findings - new development iteration |  | TBA
Industry |  | Review with stakeholders |  | TBA
|  | Total Hours: | 26 | 0

## Halfway Report
Industry | Deliverables | Activity | Estimated Time (hrs) | Actual Time (hrs)
Academic | Curriculum Vitea and Cover Letter | Updating CV and Cover Letter for the possible projects | 3 | 5
Academic | WIL and Supporting Documents | Signed by people involved |  | 2
Academic | Weekly Academic Supervisor Meetings | Weekly review of Risk Assessment, Burndown Chart and Progress Report | 0.75 | 0.75
Academic | Project Proposal | Project Details | 2 | 2
Academic |  | Project Scope | 1 | 1
Academic |  | Stakeholder Management | 2 | 2
Academic |  | Student Required Skills | 2 | 2
Academic |  | Project Plan | 2 | 2
Academic |  | Burndown Chart | 2 | 2
Academic |  | Risk Management | 2 | 2
Academic |  | Quality Assurance | 2 | 2
Academic |  | Professionalism | 2 | 2
Academic |  | Sustainability, Inclusive Practive and Te Tiriti o Waitangi | 3 | 3
Academic |  | Reflections | 2 | 0
Academic |  | References | 2 | 1
Academic |  | Appendices | 2 | 1
Academic | Weekly Academic Supervisor Meetings | Weekly check in | 0.75 | 0.75
Academic | Weekly Academic Supervisor Meetings | Weekly check in | 0.75 | 0.75
Academic | Weekly Academic Supervisor Meetings | Weekly check in | 0.75 | 0.75
Academic | Project Proposal Checklist | Checking requirements needed for checklist | 1 | TBA
Academic | Project Proposal Signoff | Following Ara's sign off document | 1 | 1
Academic | Project Proposal Update | Update Project Proposal based on Feedback from David | 10 | 30
Academic | Halfway Repport | Progress update, reflections, what went well and didn't go well, improvements | 10 | 30
Academic | Methodology Essay | 3,000 word document covers the topics in the marking guide based on the projects Methodology - Kanban | 10 | TBA
Academic | Final Report | Final reflections and self evaluation | 10 | TBA
Academic |  | Review final report document | 2 | TBA
Academic |  | Get and Apply feedback | 30 | TBA
Academic | Short Paper | Includes Introduction, Title, Author, Methodology, Process, Conclusions and Reflections | 10 | TBA
Academic | Poster | A1 format poster including: Introduction, Title, Author, Methodology, Process, Conclusions and Reflections | 10 | TBA
Academic | Short Biography | Professional writing of background and achievements | 10 | TBA
Academic | Panel Presentation | Creating Powerpoint | 10 | TBA
|  | Practice for presentation | 3 | TBA
|  | Presentation | 1 | TBA
|  | Total Hours: | 150 | 93
Industry | Discovery | Find out what is currently being used | 2 | 0.5
Industry |  | Find out what data is needed | 2 | 2
Industry |  | Find out how SharePoint works | 5 | 5
Industry |  | Find out how Power Apps works | 20 | 10
Industry |  | Find out how Power Automate Works | 20 | 10
Industry |  | Find out how Power BI works | 20 | 10
Industry | Design | Generate iterations of low-fi design | 5 | 10
Industry |  | Get feedback | 1 | 1
Industry |  | Generate iterations of low-fi design | 5 | 5
Industry |  | Get feedback | 1 | 1
Industry |  | Generate iterations of low-fi design | 5 | 5
Industry |  | Get feedback | 1 | 1
Industry |  | Generate data flow | 5 | 15
Industry |  | Get feedback | 1 | 1
Industry |  | Generate final design | 2 | 1
Industry |  | Generate final data flow | 2 | 0
Industry | Iteration One | Have weekly meeding | 1 | 1
Industry |  | Check and Update with MS Planner | 1 | 1
Industry |  | Plan for iteration | 1 | 1
Industry |  | Build iteration | 30 | 60
Industry |  | Get feedback | 1 | 1
Industry |  | Apply feedback | 5 | 1
Industry |  | Create development document for iteration | 5 | 0
Industry | Iteration Two | Have weekly meeding | 1 | 1
Industry |  | Check with MS Planner | 1 | 1
Industry |  | Plan for iteration | 1 | 1
Industry |  | Build iteration | 15 | TBA
Industry |  | Get feedback | 1 | TBA
Industry |  | Apply feedback | 5 | TBA
Industry |  | Create development document for iteration | 5 | TBA
Industry | Iteration Three | Have weekly meeding | 1 | TBA
Industry |  | Check with MS Planner | 1 | TBA
Industry |  | Plan for iteration | 1 | TBA
Industry |  | Build iteration | 30 | TBA
Industry |  | Get feedback | 1 | TBA
Industry |  | Apply feedback | 5 | TBA
Industry |  | Create development document for iteration | 5 | TBA
Industry | Iteration Four | Have weekly meeding | 1 | TBA
Industry |  | Check with MS Planner | 1 | TBA
Industry |  | Plan for iteration | 1 | TBA
Industry |  | Build iteration | 15 | TBA
Industry |  | Get feedback | 1 | TBA
Industry |  | Apply feedback | 5 | TBA
Industry |  | Create development document for iteration | 5 | TBA
Industry | Iteration Five | Have weekly meeding | 1 | TBA
Industry |  | Check with MS Planner | 1 | TBA
Industry |  | Plan for iteration | 1 | TBA
Industry |  | Build iteration | 15 | TBA
Industry |  | Get feedback | 1 | TBA
Industry |  | Apply feedback | 5 | TBA
Industry | Iteration Six | Have weekly meeding | 1 | TBA
Industry |  | Check with MS Planner | 1 | TBA
Industry |  | Plan for iteration | 1 | TBA
Industry |  | Build iteration | 15 | TBA
Industry |  | Get feedback | 1 | TBA
Industry |  | Apply feedback | 5 | TBA
Industry |  | Create development document for iteration | 5 | TBA
Industry | Iteration Six | Have weekly meeding | 1 | TBA
Industry |  | Check with MS Planner | 1 | TBA
Industry |  | Plan for iteration | 1 | TBA
Industry |  | Build iteration | 15 | TBA
Industry |  | Get feedback | 1 | TBA
Industry |  | Apply feedback | 5 | TBA
|  | Total Hours: | 320 | 145.5

## Final Report
Industry | Deliverables | Activity | Estimated Time (hrs) | Actual Time (hrs)
Academic | Curriculum Vitea and Cover Letter | Updating CV and Cover Letter for the possible projects | 3 | 5
Academic | WIL and Supporting Documents | Signed by people involved |  | 2
Academic | Weekly Academic Supervisor Meetings | Weekly review of Risk Assessment, Burndown Chart and Progress Report | 0.75 | 0.75
Academic | Project Proposal | Project Details | 2 | 2
Academic |  | Project Scope | 1 | 1
Academic |  | Stakeholder Management | 2 | 2
Academic |  | Student Required Skills | 2 | 2
Academic |  | Project Plan | 2 | 2
Academic |  | Burndown Chart | 2 | 2
Academic |  | Risk Management | 2 | 2
Academic |  | Quality Assurance | 2 | 2
Academic |  | Professionalism | 2 | 2
Academic |  | Sustainability, Inclusive Practive and Te Tiriti o Waitangi | 3 | 3
Academic |  | Reflections | 2 | 0
Academic |  | References | 2 | 1
Academic |  | Appendices | 2 | 1
Academic | Weekly Academic Supervisor Meetings | Weekly check in | 0.75 | 0.75
Academic | Weekly Academic Supervisor Meetings | Weekly check in | 0.75 | 0.75
Academic | Weekly Academic Supervisor Meetings | Weekly check in | 0.75 | 0.75
Academic | Project Proposal Checklist | Checking requirements needed for checklist | 1 | TBA
Academic | Project Proposal Signoff | Following Ara's sign off document | 1 | 1
Academic | Project Proposal Update | Update Project Proposal based on Feedback from David | 10 | 30
Academic | Halfway Repport | Progress update, reflections, what went well and didn't go well, improvements | 10 | 30
Academic | Methodology Essay | 3,000 word document covers the topics in the marking guide based on the projects Methodology - Kanban | 10 | TBA
Academic | Final Report | Final reflections and self evaluation | 10 | TBA
Academic |  | Review final report document | 2 | TBA
Academic |  | Get and Apply feedback | 30 | TBA
Academic | Short Paper | Includes Introduction, Title, Author, Methodology, Process, Conclusions and Reflections | 10 | TBA
Academic | Poster | A1 format poster including: Introduction, Title, Author, Methodology, Process, Conclusions and Reflections | 10 | TBA
Academic | Short Biography | Professional writing of background and achievements | 10 | TBA
Academic | Panel Presentation | Creating Powerpoint | 10 | TBA
|  | Practice for presentation | 3 | TBA
|  | Presentation | 1 | TBA
|  | Total Hours: | 150 | 93
Industry | Discovery | Find out what is currently being used | 2 | 0.5
Industry |  | Find out what data is needed | 2 | 2
Industry |  | Find out how SharePoint works | 5 | 5
Industry |  | Find out how Power Apps works | 20 | 10
Industry |  | Find out how Power Automate Works | 20 | 10
Industry |  | Find out how Power BI works | 20 | 10
Industry | Design | Generate iterations of low-fi design | 5 | 10
Industry |  | Get feedback | 1 | 1
Industry |  | Generate iterations of low-fi design | 5 | 5
Industry |  | Get feedback | 1 | 1
Industry |  | Generate iterations of low-fi design | 5 | 5
Industry |  | Get feedback | 1 | 1
Industry |  | Generate data flow | 5 | 15
Industry |  | Get feedback | 1 | 1
Industry |  | Generate final design | 2 | 1
Industry |  | Generate final data flow | 2 | 0
Industry | Iteration One | Have weekly meeding | 1 | 1
Industry |  | Check and Update with MS Planner | 1 | 1
Industry |  | Plan for iteration | 1 | 1
Industry |  | Build iteration | 30 | 60
Industry |  | Get feedback | 1 | 1
Industry |  | Apply feedback | 5 | 1
Industry |  | Create development document for iteration | 5 | 0
Industry | Iteration Two | Have weekly meeding | 1 | 1
Industry |  | Check with MS Planner | 1 | 1
Industry |  | Plan for iteration | 1 | 1
Industry |  | Build iteration | 15 | TBA
Industry |  | Get feedback | 1 | TBA
Industry |  | Apply feedback | 5 | TBA
Industry |  | Create development document for iteration | 5 | TBA
Industry | Iteration Three | Have weekly meeding | 1 | TBA
Industry |  | Check with MS Planner | 1 | TBA
Industry |  | Plan for iteration | 1 | TBA
Industry |  | Build iteration | 30 | TBA
Industry |  | Get feedback | 1 | TBA
Industry |  | Apply feedback | 5 | TBA
Industry |  | Create development document for iteration | 5 | TBA
Industry | Iteration Four | Have weekly meeding | 1 | TBA
Industry |  | Check with MS Planner | 1 | TBA
Industry |  | Plan for iteration | 1 | TBA
Industry |  | Build iteration | 15 | TBA
Industry |  | Get feedback | 1 | TBA
Industry |  | Apply feedback | 5 | TBA
Industry |  | Create development document for iteration | 5 | TBA
Industry | Iteration Five | Have weekly meeding | 1 | TBA
Industry |  | Check with MS Planner | 1 | TBA
Industry |  | Plan for iteration | 1 | TBA
Industry |  | Build iteration | 15 | TBA
Industry |  | Get feedback | 1 | TBA
Industry |  | Apply feedback | 5 | TBA
Industry | Iteration Six | Have weekly meeding | 1 | TBA
Industry |  | Check with MS Planner | 1 | TBA
Industry |  | Plan for iteration | 1 | TBA
Industry |  | Build iteration | 15 | TBA
Industry |  | Get feedback | 1 | TBA
Industry |  | Apply feedback | 5 | TBA
Industry |  | Create development document for iteration | 5 | TBA
Industry | Iteration Six | Have weekly meeding | 1 | TBA
Industry |  | Check with MS Planner | 1 | TBA
Industry |  | Plan for iteration | 1 | TBA
Industry |  | Build iteration | 15 | TBA
Industry |  | Get feedback | 1 | TBA
Industry |  | Apply feedback | 5 | TBA
|  | Total Hours: | 320 | 145.5