## Risk Forumulas
Risk Assessment Matrix | [5 empty] | Catastrophic (C): | Frequent (F): Probability (3) x Severity (3) = 9
Risk Assessment Matrix | [6 empty] | Likely (L): Probability (3) x Severity (3) = 9
| PROBABILITY | [5 empty] | Occasional (O): Probability (3) x Severity (2) = 6
SEVERITY | Frequent (F) | Likely (L) | Occasional (O) | Seldom (S) | Unlikely (U) |  | Seldom (S): Probability (2) x Severity (2) = 4
Unlikely (U): Probability (2) x Severity (1) = 2
Catastrophic (C) | High | High | High | Medium | Medium | Critical (CR): | Frequent (F): Probability (3) x Severity (3) = 9
Likely (L): Probability (3) x Severity (3) = 9
Critical (CR) | High | High | Medium | Medium | Low |  | Occasional (O): Probability (2) x Severity (2) = 4
Seldom (S): Probability (2) x Severity (2) = 4
Marginal (M) | High | Medium | Medium | Low | Low |  | Unlikely (U): Probability (1) x Severity (1) = 1
[6 empty] | Marginal (M): | Frequent (F): Probability (3) x Severity (2) = 6
Negligible (N) | Medium | Low | Low | Low | Low |  | Likely (L): Probability (3) x Severity (2) = 6
Occasional (O): Probability (2) x Severity (2) = 4
Seldom (S): Probability (1) x Severity (1) = 2
PROBABILITY – The likelihood that an event will occur. | [6 empty] | Unlikely (U): Probability (1) x Severity (1) = 2
FREQUENT – Occurs often, continuously experienced. | [5 empty] | Negligible (N): | Frequent (F): Probability (2) x Severity (1) = 2
LIKELY – Occurs several times. | [6 empty] | Likely (L): Probability (1) x Severity (1) = 1
OCCASIONAL – Occurs sporadically. | [6 empty] | Occasional (O): Probability (1) x Severity (1) = 1
SELDOM – Unlikely, but could occur at some time. | [6 empty] | Seldom (S): Probability (1) x Severity (1) = 1
UNLIKELY – Can assume it will not occur. | [6 empty] | Unlikely (U): Probability (1) x Severity (1) = 1
SEVERITY – The expected consequence of an event on the project.
CATASTROPHIC – Project failure.
CRITICAL –Major system outage, significant project delay or cost increase.
MARGINAL – Minor system outage, minor project delay or cost increase.
NEGLIGIBLE – Little/no impact on project accomplishment.
RISK
H – High
M –Medium
L – Low
High | 3
Medium | 2
Low | 1

## Event Log
| Cello Project : Event Log | [7 empty] | Jared Ireland
2023-10-02
Date removed | Risk Table Number | Date Removed | Risk ID | Risk Description | Issue | Probability | Severity | Risk Level | Risk Response Strategy | Mitigation Actions | Status | Reason
2023-08-29 | 1 |  | 1 | Scope Creep | The project becomes to large |  |  |  | Mitigation | Discuss with project owner and industry supivisor before project start and during project to make sure defined deliverables are set and can be met within the time frame | Closed | Consolidation of Risks to be more manageable Project workload was heavily reduced
2023-08-29 | 1 |  | 8 | Vendor Issues | Issues with access to third party tools and applications |  |  |  | Acceptance | Infrom Industry and Academic of issues. Continue developing the ideas of deliverables. | Closed | Consolidation of Risks to be more manageable
2023-08-29 | 1 |  | 9 | Equipment Failure | Technological equiment failing |  |  |  | Avoidance | Ensure that there are multiple locations and devices for use | Closed | Consolidation of Risks to be more manageable
2023-08-29 | 1 |  | 10 | Inadequate Training | Time spent away from project work to learn new skills |  |  |  | Acceptance | New skills will need to be learnt during the project. Spending time on learning these prior, if possible. | Closed | Consolidation of Risks to be more manageable
| 3 | 2023-09-19 | 5 | Inaccessibility to project | Unable to work on the project due incorrect access to data, software, other tools or other reasons like natural disasters |  |  |  | Transfer | Contact Industry Supervisor, Academic Supervisor and possibly Course Convenor to develop and set out a plan for the foreseeable future | Closed | During Discovery and Design phases it was found that the current levels of software that I have access to are inadiqute to what I need. Discussed during meeting about this.
| 3 | 2023-09-20 | 8 | Health Complications of surrounding people | Unable to work for long periods of time on project work |  |  |  | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | Closed | A family member became unwell due to myself being able to be at home for the duration of their sickness I was unable to do work for lengthy periods of time reducing how much work could be done, while I was helping the sick person and taking on other household tasks. This has been closed for the week however will be reopened for the next check
| 4 | 2023-10-02 | 8 | Outdated Information on Software | Avaliable information for software is outdated |  |  |  | Acceptance | Attempt to find other routes, including decompressing what could be just one code block into many code blocks | New | Microsoft Office has changed a lot resulting in a lot of online information being outdated. Though Documentation may be up to scratch the usecases showcased, personally, have always been lackluster resulting in finding other sources of information to be found

## Risk Analysis
Risk Description | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20
Inaccessibility | 0 | 0 | 6 | 6 | 1 | 1 | 1 | 5 | 5
Personal Issues | 2 | 0 | 0 | 10 | 2 | 2 | 2 | 8 | 8
Communication Breakdown | 0 | 0 | 5 | 2 | 2 | 2 | 1 | 1 | 1
Inadequate Training | 9 | 9 | 1 | 1 | 1 | 1 | 8 | 8 | 8
Outdated Information | 0 | 0 | 10 | 10 | 9 | 2 | 1 | 1 | 1

## Risk Assessment 1
Cello Project : Risk Assessment Table | [5 empty] | Jared Ireland |  |  |  | Cello Project : Risk Assessment Table Graphing
2023-08-17
Risk ID | Risk Description | Issue | Probability | Severity | Risk Level | Risk Response Strategy | Mitigation Actions | Status | Graph Value
1 | Scope Creep | The project becomes to large | Seldom | Marginal | Low | Mitigation | Discuss with project owner and industry supivisor before project start and during project to make sure defined deliverables are set and can be met within the time frame | New | 2
2 | Data Loss | Redoing of work needing to be done and not meeting due dates | Seldom | Critical | Medium | Mitigation | Ensure that backups are being made to either private access cloud software or removable media devices (i.e. USB drive) | New | 6
3 | Sickness | Unable to work on the project | Seldom | Critical | Medium | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | New | 6
4 | Software Bugs | Delays in project work | Seldom | Critical | Medium | Mitigation | Ensure that some form of code reviewing is being done. Not dewelling on an issue and seek help from others. | New | 6
5 | Uncertain Deliverables | Developing something that is unwanted or unneeded for the outline of the project | Seldom | Marginal | Low | Mitigation | Discuss prior to project start with the Industry leads on what is required for deliverables in a clear and understanding manner as well as having daily/bidaily/weekly checkins for progress reporting | New | 2
6 | Inaccessibility to information or tools | Unable to work on the project due incorrect access to data, software or other tools | Seldom | Marginal | Low | Transfer | Contact Industry Supervisor or other member within Industry to get the right data or tools | New | 2
7 | Communication Breakdown | Unable to get in contact with needed people | Seldom | Marginal | Low | Avoidance | Ensure that there are multiple routes of contact with many people | New | 2
8 | Vendor Issues | Issues with access to third party tools and applications | Seldom | Marginal | Low | Acceptance | Infrom Industry and Academic of issues. Continue developing the ideas of deliverables. | New | 2
9 | Equipment Failure | Technological equiment failing | Seldom | Marginal | Low | Avoidance | Ensure that there are multiple locations and devices for use | New | 2
10 | Inadequate Training | Time spent away from project work to learn new skills | Seldom | Marginal | Low | Acceptance | New skills will need to be learnt during the project. Spending time on learning these prior, if possible. | New | 2

## Risk Assessment 2
Cello Project : Risk Assessment Table | [5 empty] | Jared Ireland
2023-08-29
Risk ID | Risk Description | Issue | Probability | Severity | Risk Level | Risk Response Strategy | Mitigation Actions | Status | Graph Value
1 | Data Loss | Redoing of work needing to be done and not meeting due dates | Seldom | Critical | Medium | Mitigation | Ensure that backups are being made to either private access cloud software (git repos) or removable media devices (i.e. USB drive) | Open | 6
2 | Sickness | Unable to work on the project | Seldom | Critical | Medium | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | Open | 6
3 | Software Bugs | Delays in project work | Seldom | Critical | Medium | Mitigation | Ensure that some form of code reviewing is being done. Not dewelling on an issue and seek help from others. | Open | 6
4 | Uncertainty around Project Requirements | Developing something that is unwanted or unneeded for the outline of the project | Seldom | Marginal | Low | Mitigation | Discuss prior to project start with the Industry leads on what is required for deliverables in a clear and understanding manner as well as having weekly checkins for progress reporting | Open | 2
5 | Inaccessibility to project | Unable to work on the project due incorrect access to data, software, other tools or other reasons like natural disasters | Seldom | Marginal | Low | Transfer | Contact Industry Supervisor, Academic Supervisor and possibly Course Convenor to develop and set out a plan for the foreseeable future | Open | 2
6 | Communication Breakdown | Unable to get in contact with needed people | Seldom | Marginal | Low | Avoidance | Ensure that there are multiple routes of contact with many people | Open | 2
7 | Health Complications | Unable to work on the project due to health issues | Seldom | Marginal | Low | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | New | 2

## Risk Assessment 3
Cello Project : Risk Assessment Table | [5 empty] | Jared Ireland
2023-09-18
Risk ID | Risk Description | Issue | Probability | Severity | Risk Level | Risk Response Strategy | Mitigation Actions | Status | Graph Value
1 | Data Loss | Redoing of work needing to be done and not meeting due dates | Seldom | Critical | Medium | Mitigation | Ensure that backups are being made to either private access cloud software (git repos) or removable media devices (i.e. USB drive) | Open | 6
2 | Sickness | Unable to work on the project | Seldom | Critical | Medium | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | Open | 6
3 | Software Bugs | Delays in project work | Seldom | Critical | Medium | Mitigation | Ensure that some form of code reviewing is being done. Not dewelling on an issue and seek help from others. | Open | 6
4 | Uncertainty around Project Requirements | Developing something that is unwanted or unneeded for the outline of the project | Seldom | Marginal | Low | Mitigation | Discuss prior to project start with the Industry leads on what is required for deliverables in a clear and understanding manner as well as having weekly checkins for progress reporting | Open | 2
5 | Inaccessibility to project | Unable to work on the project due incorrect access to data, software, other tools or other reasons like natural disasters | Seldom | Marginal | Low | Transfer | Contact Industry Supervisor, Academic Supervisor and possibly Course Convenor to develop and set out a plan for the foreseeable future | Closed | 2
6 | Communication Breakdown | Unable to get in contact with needed people | Seldom | Marginal | Low | Avoidance | Ensure that there are multiple routes of contact with many people | Open | 2
7 | Health Complications | Unable to work on the project due to health issues | Seldom | Marginal | Low | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | Open | 2
8 | Health Complications of surrounding people | Unable to work for long periods of time on project work | Occasional | Critical | Medium | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | Closed | 18

## Risk Assessment 4
Cello Project : Risk Assessment Table | [5 empty] | Jared Ireland
2023-10-02
Risk ID | Risk Description | Issue | Probability | Severity | Risk Level | Risk Response Strategy | Mitigation Actions | Status | Graph Value
1 | Data Loss | Redoing of work needing to be done and not meeting due dates | Seldom | Critical | Medium | Mitigation | Ensure that backups are being made to either private access cloud software (git repos) or removable media devices (i.e. USB drive) | Open | 6
2 | Sickness | Unable to work on the project | Seldom | Critical | Medium | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | Open | 6
3 | Software Bugs | Delays in project work | Seldom | Critical | Medium | Mitigation | Ensure that some form of code reviewing is being done. Not dewelling on an issue and seek help from others. | Open | 6
4 | Uncertainty around Project Requirements | Developing something that is unwanted or unneeded for the outline of the project | Seldom | Marginal | Low | Mitigation | Discuss prior to project start with the Industry leads on what is required for deliverables in a clear and understanding manner as well as having weekly checkins for progress reporting | Open | 2
5 | Inaccessibility to project | Unable to work on the project due incorrect access to data, software, other tools or other reasons like natural disasters | Seldom | Marginal | Low | Transfer | Contact Industry Supervisor, Academic Supervisor and possibly Course Convenor to develop and set out a plan for the foreseeable future | Open | 2
6 | Communication Breakdown | Unable to get in contact with needed people | Seldom | Marginal | Low | Avoidance | Ensure that there are multiple routes of contact with many people | Open | 2
7 | Health Complications | Unable to work on the project due to health issues | Seldom | Marginal | Low | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | Open | 2
8 | Outdated Information on Software | Avaliable information for software is outdated | Seldom | Critical | Medium | Acceptance | Attempt to find other routes, including decompressing what could be just one code block into many code blocks | New | 6
9 | Health Complications of surrounding people | Unable to work for long periods of time on project work | Seldom | Critical | Medium | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | Open | 6
0

## Risk Assessment 5
Cello Project : Risk Assessment Table | [5 empty] | Jared Ireland
2023-10-18
Risk ID | Risk Description | Issue | Probability | Severity | Risk Level | Risk Response Strategy | Mitigation Actions | Status | Graph Value
1 | Data Loss | Redoing of work needing to be done and not meeting due dates | Seldom | Critical | Medium | Mitigation | Ensure that backups are being made to either private access cloud software (git repos) or removable media devices (i.e. USB drive) | Open | 6
2 | Sickness | Unable to work on the project | Seldom | Critical | Medium | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | Open | 6
3 | Software Bugs | Delays in project work | Seldom | Critical | Medium | Mitigation | Ensure that some form of code reviewing is being done. Not dewelling on an issue and seek help from others. | Open | 6
4 | Uncertainty around Project Requirements | Developing something that is unwanted or unneeded for the outline of the project | Seldom | Marginal | Low | Mitigation | Discuss prior to project start with the Industry leads on what is required for deliverables in a clear and understanding manner as well as having weekly checkins for progress reporting | Open | 2
5 | Inaccessibility to project | Unable to work on the project due incorrect access to data, software, other tools or other reasons like natural disasters | Seldom | Marginal | Low | Transfer | Contact Industry Supervisor, Academic Supervisor and possibly Course Convenor to develop and set out a plan for the foreseeable future | Open | 2
6 | Communication Breakdown | Unable to get in contact with needed people | Seldom | Marginal | Low | Avoidance | Ensure that there are multiple routes of contact with many people | Open | 2
7 | Health Complications | Unable to work on the project due to health issues | Seldom | Marginal | Low | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | Open | 2
8 | Outdated Information on Software | Avaliable information for software is outdated | Seldom | Critical | Medium | Acceptance | Attempt to find other routes, including decompressing what could be just one code block into many code blocks | New | 6
9 | Health Complications of surrounding people | Unable to work for long periods of time on project work | Seldom | Critical | Medium | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | Open | 6
10 | Recreation of work | Various issues can cause this risk to happen which results ito the "wanting" of recreating a lot of work, primarily caused by new knowledge and insights that has happened through the development phase | Seldom | Critical | Medium | Acceptance | Pivot to the change now and make tweaks as needed only after the completion of the current iteration go back and make the changes - count towards a new iteration | Open | 6