## Sheet1
Academic/ Industry | Deliverables | Activity | Estimated Time (hrs) | Actual Time (hrs) | Target Date Completion | Actual Date Completion
Academic | Curriculum Vitea and Cover Letter | Updating CV and Cover Letter for the possible projects | 3 | 5 | 2023-07-04 | 2023-07-04
Academic | WIL and Supporting Documents | Signed by people involved |  |  | 2023-08-25 | TBA
Academic | Weekly Academic Supervisor Meetings | Weekly review of Risk Assessment, Burndown Chart and Progress Report | TBA | TBA | TBA | TBA
Academic | Project Proposal | Project Details | 2 | 2 | 2023-08-25 | TBA
Academic |  | Project Scope | 1 | 1
Academic |  | Stakeholder Management | 2 | 2
Academic |  | Student Required Skills | 2
Academic |  | Project Plan | 2
Academic |  | Burndown Chart | 2
Academic |  | Risk Management | 2
Academic |  | Quality Assurance | 2
Academic |  | Professionalism | 2
Academic |  | Sustainability, Inclusive Practive and Te Tiriti o Waitangi | 3
Academic |  | Reflections | 2
Academic |  | References | 2
Academic |  | Appendices | 2
Academic | Project Proposal Checklist | Checking requirements needed for checklist | 1 | TBA | 2023-08-25 | TBA
Academic | Project Proposal Signoff | Following Ara's sign off document | 1 | TBA | 2023-08-25 | TBA
Academic | Halfway Repport | Progress update, reflections, what went well and didn't go well, improvements | TBA | TBA | TBA | TBA
Academic | Methodology Essay | 3,000 word document covers the topics in the marking guide based on the projects Methodology - Kanban | 10 | TBA | TBA | TBA
Academic | Final Report | Final reflections and self evaluation | 5 | TBA | TBA | TBA
Academic |  | Review final report document | 2 | TBA
Academic |  | Get feedback | 3 | TBA
Academic | Short Paper | Includes Introduction, Title, Author, Methodology, Process, Conclusions and Reflections | 5 | TBA | TBA | TBA
Academic | Poster | A1 format poster including: Introduction, Title, Author, Methodology, Process, Conclusions and Reflections | 5 | TBA | TBA | TBA
Academic | Short Biography | Professional writing of background and achievements | 2 | TBA | TBA | TBA
Academic | Panel Presentation | Creating Powerpoint | 5 | TBA | TBA | TBA
|  | Practive for presentation | 2 | TBA | TBA | TBA
|  | Presentation | 1 | TBA | TBA | TBA
|  | Total Hours: | 71 | 10
Industry | Discovery | Find out what is currently being used | 2 | TBA | TBA | TBA
Industry |  | Find out what data is needed | 2 | TBA | TBA | TBA
Industry |  | Find out how SharePoint works | 20 | TBA | TBA | TBA
Industry |  | TBA | TBA | TBA | TBA | TBA
Industry |  | TBA | TBA | TBA | TBA | TBA
Industry |  | TBA | TBA | TBA | TBA | TBA
Industry |  | TBA | TBA | TBA | TBA | TBA
Industry | Design | Generate iterations of low-fi design | 2 | TBA | TBA | TBA
Industry |  | Get feedback | 2 | TBA | TBA | TBA
Industry |  | Generate iterations of high-fi design | 5 | TBA | TBA | TBA
Industry |  | Get feedback | 2 | TBA | TBA | TBA
Industry |  | Generate user tests | 5 | TBA | TBA | TBA
Industry |  | Get feedback | 2 | TBA | TBA | TBA
Industry |  | TBA | TBA | TBA | TBA | TBA
Industry | Develop and Build (Per iteration) | Have weekly meeding | 1 | TBA | TBA | TBA
Industry |  | Check with MS Planner | 1 | TBA | TBA | TBA
Industry |  | Plan for iteration | 1 | TBA | TBA | TBA
Industry |  | Build iteration | 15 | TBA | TBA | TBA
Industry |  | Get feedback | 1 | TBA | TBA | TBA
Industry |  | Apply feedback | 5 | TBA | TBA | TBA
Industry |  | Create development document for iteration | 5 | TBA | TBA | TBA
Industry | Test and Review | Plan software tests | 2 | TBA | TBA | TBA
Industry |  | Plan user tests | 2 | TBA | TBA | TBA
Industry |  | Develop software tests | 5 | TBA | TBA | TBA
Industry |  | Develop user tests | 5 | TBA | TBA | TBA
Industry |  | Apply test findings - new development iteration | 10 | TBA | TBA | TBA
Industry |  | Review with Stakeholders | 1 | TBA | TBA | TBA
|  | Total Hours: | 96 | 0