## Industry Quality Assurance
Project Deliverables | Deliverable Quality Standard | Quality Assurance Activity | Frequency | Signee/s | Date of Acceptance
Weekly Progress Meetings | Meet with Industry Supervisor/s to indicate progress of work | Present current progress Ask questions if stuck on any tasks | Weekly | Jodi Anderson / Stephen Penfold | TBA
SharePoint Design | Industry Supervisor/s checking of SharePoint Design | Meeting with Industry Supervisor/s to check with the design and flow of the SharePoint site and get acceptance | As needed | Jodi Anderson / Stephen Penfold | TBA
SharePoint Creation | Creating the SharePoint page based on design | Meeting with Industry Supervisor/s to get acceptance | As needed | Jodi Anderson / Stephen Penfold | TBA
Connection with AutoCello | Successfully pulling information from AutoCello | Being able to successfully pull correct information from AutoCello and be able to use its data without causing overloading issues | As needed | Jodi Anderson / Stephen Penfold | TBA
Displaying staff leave | Successfully getting Staff Leave from AutoCello | Implementing a connection between AutoCello and a Database to hold and display Staff Leave dates | As needed | Jodi Anderson / Stephen Penfold | TBA
Calender Management - NOC | Implementation of NOC Projects | Implementing a connection between Office 365 and the Departments calendar and displaying the information in the primary calender on the SharePoint Page | As needed | Jodi Anderson / Stephen Penfold | TBA
Calener Management - WAN | Implementation of WAN Projects |  | As needed | Jodi Anderson / Stephen Penfold | TBA
Calender Management - LAN | Implementation of LAN Projects |  | As needed | Jodi Anderson / Stephen Penfold | TBA
Calender Management - Security | Implementation of Security Projects |  | As needed | Jodi Anderson / Stephen Penfold | TBA
Booking System | Implemen a booking system for staff to book other staff | Implementation of a booking system that will allow staff to book other needed staff out, sending the booked staff member an email and updating their calendar | As needed | Jodi Anderson / Stephen Penfold | TBA
Filtering Calendar | Implementing a filter for the calendar | Implementing a filter for staff to say what department they are from, what department they need and the starting and ending dates | As needed | Jodi Anderson / Stephen Penfold | TBA
Documentation of project | Document on how the project works | Documenting how the project works so other staff members in the future are able to add, update and tweak where need be | As needed | Jodi Anderson / Stephen Penfold | TBA

## Academic Quality Assurance
Project Deliverables | Deliverable Quality Standard | Quality Assurance Activity | Frequency | Signee/s | Date of Acceptance
Curriculum Vitae and Cover Letter | Professionally Written | Discuss with Carrers | Once | Jared Ireland | 2023-07-28
WIL Agreement and Supporting documents | Signed by people involved with the project | Download WIL Agreement and send to industry supervisor. After reciving the industry signature sending to academic supervisor | Once | Jodi Anderson Peter Edge Dr David Weir Jared Ireland | TBA
Weekly Meeting Reviews | Submit and review: Risk Management Burndown Chart Industry Quality Assurance | Esure that documents are prepared for review | Weekly | Peter Edge Jared Ireland | TBA
Project Proposal | Follow Ara Guidelines Follow APA v7 Referencing Guide Use provided Template | Academic and Industry Supervisors feedback Follow Assessment marking rubric | As necessary | Jodi Anderson Peter Edge Dr David Weir Jared Ireland | TBA
Project Proposal Checklist | Follow Ara provided checklist | Ensure all requirements have been checked off | As necessary | Jared Ireland | TBA
Project Proposal Sign Off | Follow Ara provided sign off | Ensure that the project proposal is appropriate based on project requirements | Once | Jodi Anderson Peter Edge Dr David Weir Jared Ireland | TBA
Timeline and Burndown Chart | Burndown consisting of Predicted and Actual time, in hours, for Academic and Industry work | Academic Superviosr review and feedback | As necessary | Peter Edge Jared Ireland | TBA
Risk Assessment | Risk assessment of the project | Version controlling of Risks Academic Superviosr review and feedback | As necessary | Peter Edge Jared Ireland | TBA
Halfway Report | Document progress of what I have completed | Academic and Industry Supervisors feedback Follow Assessment marking rubric | As necessary | Jodi Anderson Peter Edge Dr David Weir Jared Ireland | TBA
Methodology Essay | 3000 Word Document covering topics listed in Marking Guide | Academic and Industry Supervisors feedback Follow Assessment marking rubric | As necessary | Jodi Anderson Peter Edge Dr David Weir Jared Ireland | TBA
Final Report | Final reflections and self evaluation based on Panel Assessment marking guide. | Academic and Industry Supervisors feedback Follow Assessment marking rubric | As necessary | Jodi Anderson Peter Edge Dr David Weir Jared Ireland | TBA
Short Paper Project Poster | Including: Introduction Title Author Methodology Process Conclusion References | Academic and Industry Supervisors feedback Follow Assessment marking rubric | As necessary | Jodi Anderson Peter Edge Dr David Weir Jared Ireland | TBA
Short Bio | Professional document of background and achievements | Academic and Industry Supervisors feedback Follow Assessment marking rubric | As necessary | Jodi Anderson Peter Edge Dr David Weir Jared Ireland | TBA
Panel Presentation | Powerpoint presentaton to be submitted | Follow Assessment marking rubric | Once | TBD | TBA