## Risk Forumulas
An Example Risk Assessment Matrix
Risk Assessment Matrix
PROBABILITY
SEVERITY | Frequent (F) | Likely (L) | Occasional (O) | Seldom (S) | Unlikely (U)
Catastrophic (C) | H | H | H | M | M
Critical (CR) | H | H | M | M | L
Marginal (M) | H | M | M | L | L
Negligible (N) | M | L | L | L | L
PROBABILITY – The likelihood that an event will occur.
FREQUENT – Occurs often, continuously experienced.
LIKELY – Occurs several times.
OCCASIONAL – Occurs sporadically.
SELDOM – Unlikely, but could occur at some time.
UNLIKELY – Can assume it will not occur.
SEVERITY – The expected consequence of an event on the project.
CATASTROPHIC – Project failure.
CRITICAL –Major system outage, significant project delay or cost increase.
MARGINAL – Minor system outage, minor project delay or cost increase.
NEGLIGIBLE – Little/no impact on project accomplishment.
RISK
H – High
M –Medium
L – Low

## Event Log
| Cello Project : Event Log | [6 empty] | Jared Ireland
2023-08-17
Date removed | Risk Table Number | Risk ID | Risk Description | Issue | Likelihood | Impact | Priority | Risk Response Strategy | Mitigation Actions | Status | Reason
2023-08-29 | 1 | 1 | Scope Creep | The project becomes to large | Medium | High | High | Mitigation | Discuss with project owner and industry supivisor before project start and during project to make sure defined deliverables are set and can be met within the time frame | Closed | Consolidation of Risks to be more manageable Project workload was heavily reduced
2023-08-29 | 1 | 8 | Vendor Issues | Issues with access to third party tools and applications | Medium | Low | Low | Acceptance | Infrom Industry and Academic of issues. Continue developing the ideas of deliverables. | Closed | Consolidation of Risks to be more manageable
2023-08-29 | 1 | 9 | Equipment Failure | Technological equiment failing | Low | High | Medium | Avoidance | Ensure that there are multiple locations and devices for use | Closed | Consolidation of Risks to be more manageable
2023-08-29 | 1 | 10 | Inadequate Training | Time spent away from project work to learn new skills | High | Medium | High | Acceptance | New skills will need to be learnt during the project. Spending time on learning these prior, if possible. | Closed | Consolidation of Risks to be more manageable

## Risk Assessment 1
Cello Project : Risk Assessment Table | [5 empty] | Jared Ireland
2023-08-17
Risk ID | Risk Description | Issue | Likelihood | Impact | Priority | Risk Response Strategy | Mitigation Actions | Status
1 | Scope Creep | The project becomes to large | Medium | High | High | Mitigation | Discuss with project owner and industry supivisor before project start and during project to make sure defined deliverables are set and can be met within the time frame | New
2 | Data Loss | Redoing of work needing to be done and not meeting due dates | Low | High | Medium | Mitigation | Ensure that backups are being made to either private access cloud software or removable media devices (i.e. USB drive) | New
3 | Sickness | Unable to work on the project | Low | Low | Low | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | New
4 | Software Bugs | Delays in project work | High | Low | Medium | Mitigation | Ensure that some form of code reviewing is being done. Not dewelling on an issue and seek help from others. | New
5 | Uncertain Deliverables | Developing something that is unwanted or unneeded for the outline of the project | Medium | Medium | Medium | Mitigation | Discuss prior to project start with the Industry leads on what is required for deliverables in a clear and understanding manner as well as having daily/bidaily/weekly checkins for progress reporting | New
6 | Inaccessibility to information or tools | Unable to work on the project due incorrect access to data, software or other tools | Medium | Medium | Medium | Transfer | Contact Industry Supervisor or other member within Industry to get the right data or tools | New
7 | Communication Breakdown | Unable to get in contact with needed people | Medium | Medium | Medium | Avoidance | Ensure that there are multiple routes of contact with many people | New
8 | Vendor Issues | Issues with access to third party tools and applications | Medium | Low | Low | Acceptance | Infrom Industry and Academic of issues. Continue developing the ideas of deliverables. | New
9 | Equipment Failure | Technological equiment failing | Low | High | Medium | Avoidance | Ensure that there are multiple locations and devices for use | New
10 | Inadequate Training | Time spent away from project work to learn new skills | High | Medium | High | Acceptance | New skills will need to be learnt during the project. Spending time on learning these prior, if possible. | New

## Risk Assessment 2
Cello Project : Risk Assessment Table | [5 empty] | Jared Ireland
2023-08-29
Risk ID | Risk Description | Issue | Likelihood | Impact | Priority | Risk Response Strategy | Mitigation Actions | Status
1 | Data Loss | Redoing of work needing to be done and not meeting due dates | Low | High | Medium | Mitigation | Ensure that backups are being made to either private access cloud software (git repos) or removable media devices (i.e. USB drive) | Open
2 | Sickness | Unable to work on the project | Low | Low | Low | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | Open
3 | Software Bugs | Delays in project work | High | Low | Medium | Mitigation | Ensure that some form of code reviewing is being done. Not dewelling on an issue and seek help from others. | Open
4 | Uncertainty around Project Requirements | Developing something that is unwanted or unneeded for the outline of the project | Medium | Medium | Medium | Mitigation | Discuss prior to project start with the Industry leads on what is required for deliverables in a clear and understanding manner as well as having weekly checkins for progress reporting | Open
5 | Inaccessibility to project | Unable to work on the project due incorrect access to data, software, other tools or other reasons like natural disasters | Medium | Medium | Medium | Transfer | Contact Industry Supervisor, Academic Supervisor and possibly Course Convenor to develop and set out a plan for the foreseeable future | Open
6 | Communication Breakdown | Unable to get in contact with needed people | Medium | Medium | Medium | Avoidance | Ensure that there are multiple routes of contact with many people | Open
7 | Health Complications | Unable to work on the project due to health issues | Will happen | Medium | Critical | Acceptance | Inform Industry and Academic person's of health issues and track it as a precaution | New